## Sheet1
SCRUM CALLS AND STANDUPS
S.NO. | DATE | SCRUM MASTER | TOPIC OF DISCUSSION, Summary
1 | 2023-11-12 | Nitin | 86-no-more and Project Requirements
2 | 2023-11-13 | Manideepika | Features to be involved - Requirements
3 | 2023-11-14 | Praveen | Discussed about some features and technical aspects of it
4 | 2023-11-15 | Nitin | Assigned tasks to each Developer, Discussed about how to prepare documentation
5 | 2023-11-20 | Praveen | Working on features and discussion
6 | 2023-11-22 | Manideepika | Working on features and discussion, Testing
7 | 2023-11-25 | Nitin | Working on features and discussion
8 | 2023-11-26 | Praveen | Merging the code and finalizing documentation